## burndown chart
Date | Ideal remaining points | Actual remaining points
2026-09-21 | 35 | 35
2026-09-28 | 27 | 35
2026-10-05 | 18 | 35
2026-10-12 | 9 | 32
2026-10-19 | 0 | 22

## Team velocity
sprint 1. metric | story points
completed | 13
Remaining | 22

## Completion ratio
Status | Story points
completed | 13
Not completed | 22
Completion ratio | 37.14%